UChicago Summer Farm Strategy Internship

8-Week Schedule | 80-Acre California Ranch

Start date: June 15, 2026
California site visit: June 28 – July 3, 2026
Time commitment: ~40 hours/week
Work mode: Primarily remote; one on-site visit (Jun 28 – Jul 3)
Existing materials: L1 and L2 site assessments; prior consultant reports; ranch production data

## Program Overview

This internship supports long-term crop planning analysis and a land use assessment for an ~80-acre ranch in California. Core workstreams include avocado block productivity (13 blocks, ~45 acres, ~4,500 trees), citrus decline and replanting strategy for ~25–30 acres of dying lemons/unused land, passionfruit sales and profitability, regenerative potential metrics (nonprofit alignment), and opportunity prioritization. Weekly check-ins with the ranch owner are expected throughout.

## Phase Overview

| Phase | Weeks | Dates (2026) | Focus |
| --- | --- | --- | --- |
| Orient & ingest | 1 | Jun 15–21 | Data inventory, L1/L2 review, research, visit prep |
| Remote prep | 2 (partial) | Jun 22–27 | Finalize visit logistics, stakeholder outreach, question lists |
| Field & validate | 2–3 | Jun 28 – Jul 5 | California visit + immediate synthesis |
| Analyze & model | 3–5 | Jul 6–Jul 19 | Avocado, citrus/land-use, passionfruit |
| Synthesize & plan | 6–7 | Jul 20–Aug 2 | Long-term crop plan + land use assessment |
| Deliver & hand off | 8 | Aug 3–9 | Final reports, tools, prioritized roadmap |

## Week 1 — June 15–21, 2026

Goal: Turn ambiguity into a structured work plan; deeply understand existing assessments and ranch data before California.

### Monday–Tuesday

Kickoff with owner: confirm priorities, data access, weekly meeting cadence, California visit logistics (Jun 28–Jul 3: flights, rental car, lodging).

Build data inventory spreadsheet: yields by block, irrigation/water, citrus decline, passionfruit sales/costs, labor, Becker Studios deliverables, consultant reports.

Read L1 and L2 site assessments end-to-end; extract soils, slope, drainage, water, constraints, recommended uses.

Sketch ranch base map: 13 avocado blocks, ~45 acres / ~4,500 trees, decline citrus (~25–30 acres), passionfruit, buildings, water infrastructure.

### Wednesday–Thursday

Regional context (Santa Barbara / Central Coast): water, labor, packout/sizing, market channels.

Methods research: LandIQ, USDA Cropland Data Layer, SSURGO, suitability scoring, yield/climate drivers—decide what to use this summer vs. defer.

Analog research: 2–3 case studies on avocado block productivity, lemon decline/replant, passionfruit economics.

Regenerative lens: note metrics for later application (compost, cover crop, carbon/water) without blocking core deliverables.

Outreach (email/call): Armando (farm tour Mon Jun 29), Giuseppe/Index Fresh (packing), White Buffalo Land Trust, optional regenerative farm visits.

### Friday

Finalize California visit itinerary (see below); confirm stakeholder availability for Jun 28–Jul 3.

Deliverable: Internship Work Plan v0.1 (projects, milestones, data gaps, visit checklist).

Weekly check-in #1 with ranch owner.

## Week 2 — June 22–27, 2026 | Remote Visit Prep

Goal: Complete logistics and pre-field synthesis before traveling Jun 28.

Book flights, lodging near ranch (Summerland/Montecito/Carpinteria), rental car.

Confirm Monday Jun 29 full-day ranch walk with Armando (farm manager).

Schedule Giuseppe/Index Fresh packing visit; draft irrigation and block-level question lists.

Research regenerative farm visit options (White Buffalo, Fairview Gardens, Wanderment Farms, Apricot Lane, Rincon).

Pre-load maps, L1/L2 PDFs, yield/water templates, camera/field notebook checklist.

Continue data inventory gaps; draft Site Visit Report outline.

## California Site Visit — June 28 – July 3, 2026

Goal: Ground-truth the ranch, meet stakeholders, benchmark markets and regenerative practices, align strategy with owner.

### Sunday, June 28 — Arrival & orient

Travel to Santa Barbara County; check in near ranch (Summerland area).

Review block map, L1/L2 highlights, and question lists for Monday ranch walk.

Optional: drive ranch perimeter if access allows; note market/restaurant context.

### Monday, June 29 — Ranch tour with Armando (farm manager)

PRIMARY FIELD DAY: Walk all 13 avocado blocks; irrigation/water infrastructure and pressure/zone notes.

Map citrus decline boundaries; photograph canopy, rootstock, and drainage trouble spots.

Passionfruit areas: trellis condition, production zones, harvest logistics.

Buildings, roads, water tanks/pumps, meter locations; collect any undigitized yield or irrigation records.

Geotag photos by block ID; end-of-day structured field notes.

### Tuesday, June 30 — Packing + markets

Morning: Meeting with Giuseppe (Index Fresh) — grades, rejects, sizing, pricing, returns, packout economics.

Midday: Summerland District Market (Memorial Park, 9999 Wharton St) — 9:00 AM–2:00 PM; passionfruit/specialty crop pricing and positioning.

Evening (optional): Old Town Santa Barbara Farmers Market (Lower State St, 600–800 blocks) — 3:00–6:30 PM.

### Wednesday, July 1 — Regenerative benchmarks & local partners

White Buffalo Land Trust (Summerland/Greenwell area) — regenerative organic practices; partnership potential across the street from ranch.

Fairview Gardens (Goleta) — organic/biodynamic community farm; education and programming models.

Wanderment Farms (near Santa Barbara) — pasture-raised animals, seasonal organic produce, community education.

If confirmed: Jalama Canyon Ranch (White Buffalo Savory Hub) or student shadow visit at Apricot Lane / Rincon Farms.

### Thursday, July 2 — Markets + flex field follow-up

Morning: Follow-up ranch time if needed (irrigation test, specific blocks, photo gaps) OR regenerative outreach visits.

Afternoon: Carpinteria Farmers Market (800 block Linden Ave) — 2:30–6:00 PM; compare citrus/avocado/passionfruit retail positioning.

Buffer for Index Fresh overflow meeting or owner working session.

### Friday, July 3 — Markets + strategy + departure

Morning: Montecito Farmers Market (Coast Village Rd, 1100–1200 blocks) — 8:00–11:15 AM.

Midday: Owner strategy session — Becker Studios vs. FT farm manager, capital priorities, replant timeline, organic/regenerative interest.

Afternoon: Travel home; begin converting field notes to structured log (block ID, observations, geotagged photos).

## Week 3 — June 29 – July 5, 2026 | Visit Wrap-Up + Avocado Framework Start

Goal: Close out field work (Mon–Fri on-site per itinerary above); remote synthesis Jul 4–5; begin analytical backbone for avocado investment decisions.

Jul 4–5 (remote): Convert field notes to structured log; update data inventory and gap list; digitize paper yields/irrigation notes.

Deliverables: Site Visit Report (draft); validated ranch schematic; weekly check-in #2.

As time allows: Clean avocado production by block; merge L1/L2 constraints; review consultant benchmarks.

Fri Jul 5: Define productivity metrics (lbs/tree, $/acre, trends); block scoring tiers; weekly check-in #3.

## Week 4 — July 6–12, 2026 | Avocado Productivity + Irrigation

Goal: Build owner-usable avocado dashboard and irrigation analysis.

Mon–Tue: Continue block-level cleaning and scoring; start owner-usable dashboard (Sheets/Excel).
Wed–Thu: Irrigation analysis v0.1; memo Avocado Block Productivity — Preliminary Findings.
Fri: Weekly check-in #4.

## Week 5 — July 13–19, 2026 | Citrus Decline, Land-Use Options, Geospatial Layer

Goal: Structured options analysis for ~25–30 acres of dying lemons/unused land.

Mon–Tue: Deep read prior consultant reports; market scan for viable Santa Barbara crops.
Wed–Thu: Geospatial overlay (CDL/LandIQ/SSURGO as appropriate); 3–5 scenario packages with water budgets.
Fri: Financial skeleton per scenario; start Land Use Assessment Section 2; weekly check-in #5.

## Week 6 — July 20–26, 2026 | Passionfruit Tool + Cross-Project Integration

Goal: Complete passionfruit project; align all analyses.

Mon–Tue: Design passionfruit sales & profitability tracker; backfill historical data.
Wed–Thu: Margin analysis and channel efficiency; integrate passionfruit into land-use options.
Fri: Avocado recommendations v0.2; opportunity backlog v0.1; weekly check-in #6.

## Week 7 — July 27 – August 2, 2026 | Long-Term Crop Planning Analysis (Draft)

Goal: Coherent 5–10+ year crop and rotation strategy.

Mon–Wed: Long-Term Crop Plan—current portfolio, block roadmap, phased replant timeline (Years 1–3, 4–7, 8+), water/labor trajectory, risk register.
Thu–Fri: Scenario comparison (NPV or payback where data allows); align with regenerative metrics; owner review; weekly check-in #7.

## Week 8 — August 3–9, 2026 | Land Use Assessment, Finalization & Handoff

Goal: Polished owner-ready package and sustainable tools.

Mon–Wed: Land Use Assessment—executive summary, property description, L1/L2 summary, suitability mapping, recommended spatial allocation, phasing, KPIs; Becker Studios vs. FT farm manager section.
Thu: Finalize avocado dashboard and passionfruit tracker with user guides; refine top-10 opportunity list.
Fri: Final presentation; executive deck (15–20 slides); closeout memo; weekly check-in #8.

## End-of-Internship Deliverables

| Deliverable | Target Week |
| --- | --- |
| Site Visit Report | Week 3 (draft Jul 4–5; refined Week 4) |
| Avocado block productivity framework + tool | Weeks 3–4; final Week 8 |
| Irrigation / water investment memo | Weeks 4 & 6 |
| Citrus decline & replanting options analysis | Weeks 5–6 |
| Passionfruit sales & profitability tool | Week 6; final Week 8 |
| Long-term crop planning analysis | Draft Week 7; final Week 8 |
| Land use assessment (80 acres) | Draft Week 8; final Week 8 |
| Prioritized opportunity backlog (incl. regenerative) | Weeks 6, 8 |
| Executive summary + slide deck | Week 8 |

## Suggested Weekly Rhythm (~40 hours)

| Activity | Hours/week |
| --- | --- |
| Core project work | 28–32 |
| Research & reading | 4–6 |
| Data cleaning / documentation | 4–6 |
| Owner check-in + follow-ups | 2–3 |
| Buffer for late ranch data | 2–4 |

## California Visit Checklist (confirm in Week 1–2)

Flights and lodging Jun 28–Jul 3; rental car.

Armando: Monday Jun 29 full ranch walk confirmed.

Giuseppe/Index Fresh: packing visit scheduled (target Tue Jun 30).

Owner strategy session: Friday Jul 3.

Optional: White Buffalo, Fairview Gardens, Wanderment, Apricot Lane, Rincon/Jalama outreach.

Bring: block map, L1/L2 PDFs, clipboard, camera, irrigation question list, empty yield/water templates.

## Local Farmers Markets (visit week)

Tuesday Jun 30: Summerland District Market (9 AM–2 PM) + Old Town Santa Barbara (3–6:30 PM).

Thursday Jul 2: Carpinteria (2:30–6 PM).

Friday Jul 3: Montecito (8–11:15 AM).

## Flexible Priorities

If higher-impact work emerges, protect these non-negotiable outcomes:

Land use decision framework for 25–30 acres (phased pilot + scale even if final crop TBD).

Avocado block investment map (where dollars move yield).

Owner-usable tools (passionfruit tracker + block dashboard).

Defer or lighten advanced ML pipelines unless owner requests them; geospatial methods can live in a Phase 2 appendix.

Prepared for: Max Buford | UChicago Summer Farm Strategy Internship